## Rollout Plan
Task ID | Task Name | Duration (Days) | Predecessor(s) | Start Date | End Date | Lead Resource | Status | Status Date | Notes
1 | Project Initiation & Mobilisation | 5 |  | 2026-04-20 | 2026-04-24 | Project Manager
1.1 | Project kick-off and team mobilisation | 1 | — | 2026-04-20 | 2026-04-20 | Project Manager, Business Analyst, Solution Architect | In Progress | 2026-06-02 | Team mobilised; ongoing weekly iteration with client. Client review positive.
1.2 | Set up development environments and source control | 2 | 1.1 | 2026-04-21 | 2026-04-22 | DevOps Engineer | Done | 2026-04-29 | Git repo, dotnet build/run, GitHub Actions deploy workflow operational. (2026-04-29)
1.3 | Confirm solution architecture with client stakeholders | 1 | 1.2 | 2026-04-23 | 2026-04-23 | Solution Architect, Client | In Progress | 2026-06-02 | Architecture aligned with DWS feedback; Design Amendments 001 & 002 incorporated.
1.4 | Baseline project plan and RAID log | 1 | 1.3 | 2026-04-24 | 2026-04-24 | Project Manager, Business Analyst | In Progress | 2026-06-02 | Plan baselined and now refreshed; RAID log still not maintained in tooling.
2 | Azure Infrastructure Foundation | 15 |  | 2026-04-28 | 2026-05-19 | Cloud Engineer
2.1 | Azure subscription and landing zone setup | 3 | 1.4 | 2026-04-28 | 2026-04-30 | Cloud Engineer | In Progress | 2026-06-02 | Now deployed on client Azure ('Purple Blue') tenant. Landing zone / governance not yet formalised.
2.2 | Resource groups, networking and managed identity configuration | 3 | 2.1 | 2026-05-04 | 2026-05-06 | Cloud Engineer, Security Architect
2.3 | Azure SQL Database provisioning (Dev, Test, Prod) | 2 | 2.2 | 2026-05-07 | 2026-05-08 | Cloud Engineer, Database Engineer
2.4 | Azure App Service and Blob Storage configuration | 3 | 2.3 | 2026-05-11 | 2026-05-13 | Cloud Engineer | In Progress | 2026-06-02 | App Service + GitHub Actions deploy operational on client Azure. Storage abstraction (IFileStorage) in code with local-disk impl; Azure Blob binding pending.
2.5 | Microsoft Entra ID tenancy and application registrations | 2 | 2.4 | 2026-05-14 | 2026-05-15 | Cloud Engineer, Security Architect | In Progress | 2026-06-02 | Entra ID OpenID Connect handler stubbed in Program.cs; tenant app registration pending.
2.6 | Azure Key Vault, Application Insights and Log Analytics | 2 | 2.5 | 2026-05-18 | 2026-05-19 | Cloud Engineer
3 | Access Database Migration | 7 |  | 2026-05-11 | 2026-05-19 | Database Engineer
3.1 | Inventory of legacy Access tables and data profiling | 2 | 2.3 | 2026-05-11 | 2026-05-12 | Database Engineer, Business Analyst
3.2 | Source-to-target field mapping and transformation rules | 1 | 3.1 | 2026-05-13 | 2026-05-13 | Database Engineer, Business Analyst
3.3 | Build ETL package and data cleansing routines | 2 | 3.2 | 2026-05-14 | 2026-05-15 | Database Engineer, Senior Developer
3.4 | Validation routines and reconciliation reports | 1 | 3.3 | 2026-05-18 | 2026-05-18 | Database Engineer, QA Engineer
3.5 | Rollback and cutover procedures | 1 | 3.4 | 2026-05-19 | 2026-05-19 | Database Engineer, DevOps Engineer
4 | Core Domain & Data Layer Development | 30 |  | 2026-04-28 | 2026-06-09 | Senior .NET Developer
4.1 | Finalise entity models and database schema | 5 | 1.4 | 2026-04-28 | 2026-05-05 | Solution Architect, Senior .NET Developer | In Progress | 2026-06-02 | 55+ entities incl. Workflow*, Letter*, Calculator/Lawfulness, MFA, Objection, Audit. Schema near complete (22 EF migrations).
4.2 | Entity Framework Core migrations and seed data | 3 | 4.1 | 2026-05-06 | 2026-05-08 | Senior .NET Developer, Database Engineer | Done | 2026-04-29 | Multiple EF Core migrations applied; SeedDataService + IdentitySeeder seed reference data and demo users. (2026-04-29)
4.3 | Repository layer implementation | 7 | 4.2 | 2026-05-11 | 2026-05-19 | Senior .NET Developer, .NET Developer | In Progress | 2026-06-02 | Repositories for Property, FileMaster, Owner, Address, Forestation, FieldAndCrop, DamCalculation.
4.4 | Business service layer implementation | 10 | 4.3 | 2026-05-20 | 2026-06-02 | Senior .NET Developer, .NET Developer | In Progress | 2026-06-02 | WorkflowService, LetterService, AuditService, NotificationService, plus CalculatorService (Dam/SAPWAT/SFRA) and LawfulnessAssessmentService (GWCA + general principles) all live.
4.5 | Unit tests for domain and services | 5 | 4.4 | 2026-06-03 | 2026-06-09 | .NET Developer, QA Engineer | In Progress | 2026-06-02 | ~339 unit + ViewModel test cases passing (was 79). Integration tests still need a SQL fixture.
5 | V&V Workflow Engine | 20 |  | 2026-06-10 | 2026-07-08 | Senior .NET Developer
5.1 | Case state machine (Sections 32–35 workflow) | 5 | 4.5 | 2026-06-10 | 2026-06-17 | Solution Architect, Senior .NET Developer | Done | 2026-04-29 | WorkflowEngine: CP1.1 -> CP9 state machine with 6 transition guards (CP2/3/4/5/8/9). (2026-04-29)
5.2 | Letter issuance engine (statutory letter generation and PDF) | 5 | 5.1 | 2026-06-18 | 2026-06-24 | Senior .NET Developer, Business Analyst | Done | 2026-04-29 | 10 letter templates wired (S35 L1, L1A, L2, L2A, L3, L4A, L4&5, S33(2), S33(3)(a), S33(3)(b)) rendering via QuestPDF. (2026-04-29)
5.3 | Letter service and delivery tracking | 3 | 5.2 | 2026-06-25 | 2026-06-29 | .NET Developer, Business Analyst | Done | 2026-04-29 | LetterIssuance entity tracks recipient, delivery method, issued/response dates; PDF stored in BlobStore. (2026-04-29)
5.4 | Appeals, objections and protests lifecycle | 5 | 5.3 | 2026-06-30 | 2026-07-06 | Senior .NET Developer, Business Analyst | In Progress | 2026-06-02 | Protest/Objection + ObjectionGrounds models; ExternalPortal Objection + Response flows live. Client 'Appeal/Objection' terminology adopted. Lifecycle UI iterating.
5.5 | Audit logging and compliance traceability | 2 | 5.4 | 2026-07-07 | 2026-07-08 | Senior .NET Developer | Done | 2026-06-02 | AuditLogs + AuditService write immutable rows on every workflow advance, letter issue, login, etc.
6 | Reporting & Analytics Functions | 20 |  | 2026-06-10 | 2026-07-08 | Senior .NET Developer
6.1 | Standard report development and testing | 8 | 4.5 | 2026-06-10 | 2026-06-22 | Senior .NET Developer, Business Analyst
6.2 | Ad-hoc query builder implementation | 5 | 6.1 | 2026-06-23 | 2026-06-29 | .NET Developer
6.3 | Dashboard creation and customisation | 4 | 6.2 | 2026-06-30 | 2026-07-03 | UI/UX Designer, .NET Developer
6.4 | Export functionality (Excel, PDF, CSV) | 2 | 6.3 | 2026-07-06 | 2026-07-07 | .NET Developer
6.5 | Performance optimisation for large datasets | 1 | 6.4 | 2026-07-08 | 2026-07-08 | Database Engineer, .NET Developer
7 | Advanced Features & Automation | 20 |  | 2026-07-09 | 2026-08-05 | Senior .NET Developer
7.1 | Advanced workflow automation features | 6 | 5.5, 6.5 | 2026-07-09 | 2026-07-16 | Senior .NET Developer
7.2 | Intelligent task routing implementation | 4 | 7.1 | 2026-07-17 | 2026-07-22 | Senior .NET Developer
7.3 | Automated document generation enhancement | 5 | 7.2 | 2026-07-23 | 2026-07-29 | Senior .NET Developer, Business Analyst
7.4 | Process optimisation and efficiency improvements | 3 | 7.3 | 2026-07-30 | 2026-08-03 | Senior .NET Developer, Business Analyst
7.5 | Advanced notification and reminder systems | 2 | 7.4 | 2026-08-04 | 2026-08-05 | .NET Developer
8 | User Interface Enhancement — Internal Application | 15 |  | 2026-07-09 | 2026-07-29 | UI/UX Designer
8.1 | User experience optimisation per approved wireframes | 5 | 5.5, 6.5 | 2026-07-09 | 2026-07-15 | UI/UX Designer, .NET Developer | In Progress | 2026-06-02 | Sidebar layout per latest wireframes; DWS brand palette; Appendix D dam calculator inputs added to DamCalculation views (BUG-019).
8.2 | Mobile responsiveness improvements | 3 | 8.1 | 2026-07-16 | 2026-07-20 | UI/UX Designer, .NET Developer
8.3 | Accessibility compliance (WCAG 2.1 AA) | 3 | 8.2 | 2026-07-21 | 2026-07-23 | UI/UX Designer, .NET Developer
8.4 | Performance optimisation for user interactions | 2 | 8.3 | 2026-07-24 | 2026-07-27 | .NET Developer
8.5 | User interface testing and refinement | 2 | 8.4 | 2026-07-28 | 2026-07-29 | QA Engineer, UI/UX Designer
9 | External Portal — Property Owners and Water Users | 15 |  | 2026-07-09 | 2026-07-29 | UI/UX Designer
9.1 | Portal shell, navigation and self-service registration | 4 | 5.5, 6.5 | 2026-07-09 | 2026-07-14 | UI/UX Designer, .NET Developer | Done | 2026-06-02 | Stages 1/2a/2b complete: register, email confirm, login, dashboard, case status+history, document upload, objection/response, full MFA (TOTP, SMS OTP, recovery codes, trusted device, lockout).
9.2 | Case status view and history | 3 | 9.1 | 2026-07-15 | 2026-07-17 | .NET Developer | Done | 2026-06-02 | Read-only case status view + workflow history live in external portal.
9.3 | Supporting document upload and management | 3 | 9.2 | 2026-07-20 | 2026-07-22 | .NET Developer | In Progress | 2026-06-02 | External-portal document upload live (DocumentController + IFileStorage, SHA-256 hash, virus-scan status field). Internal V&V control-point document upload now in design.
9.4 | In-app and email notification integration | 3 | 9.3 | 2026-07-23 | 2026-07-27 | .NET Developer | In Progress | 2026-06-02 | NotificationService wired for in-app + email (SMTP / logging sender); per-state-change triggers in workflow.
9.5 | Portal testing and refinement | 2 | 9.4 | 2026-07-28 | 2026-07-29 | QA Engineer, UI/UX Designer
10 | Identity, Security and POPIA Compliance | 10 |  | 2026-08-06 | 2026-08-20 | Security Architect
10.1 | Microsoft Entra ID integration and single sign-on | 3 | 7.5, 8.5, 9.5 | 2026-08-06 | 2026-08-11 | Security Architect, Senior .NET Developer | In Progress | 2026-06-02 | Entra ID OIDC path stubbed alongside Identity local accounts; full SSO not yet wired end-to-end.
10.2 | Role-based authorization and HDI indicator | 2 | 10.1 | 2026-08-12 | 2026-08-13 | Senior .NET Developer, Business Analyst | In Progress | 2026-06-02 | DwsRoles + DwsPolicies enforce RBAC (SystemAdmin/NationalManager/RegionalManager/Validator/Capturer/ReadOnly). HDI indicator on user profile (AddIsHdiToApplicationUser migration).
10.3 | POPIA compliance review and data-classification controls | 3 | 10.2 | 2026-08-14 | 2026-08-18 | Security Architect, Business Analyst
10.4 | Security hardening and threat modelling | 2 | 10.3 | 2026-08-19 | 2026-08-20 | Security Architect
11 | Solution Testing | 20 |  | 2026-08-21 | 2026-09-17 | QA Lead
11.1 | Comprehensive system testing execution | 5 | 10.4 | 2026-08-21 | 2026-08-27 | QA Lead, .NET Developer
11.2 | Performance testing with full data loads | 4 | 11.1 | 2026-08-28 | 2026-09-02 | QA Lead, Cloud Engineer
11.3 | Security testing and vulnerability assessment | 4 | 11.2 | 2026-09-03 | 2026-09-08 | Security Architect, QA Lead
11.4 | User acceptance testing coordination | 4 | 11.3 | 2026-09-09 | 2026-09-14 | QA Lead, Business Analyst, Client
11.5 | Bug fixing and system stabilisation | 3 | 11.4 | 2026-09-15 | 2026-09-17 | Senior .NET Developer, .NET Developer
12 | Azure Deployment & Go-Live | 10 |  | 2026-09-18 | 2026-10-02 | DevOps Engineer
12.1 | Production Azure environment preparation | 3 | 11.5 | 2026-09-18 | 2026-09-22 | Cloud Engineer, DevOps Engineer
12.2 | Full system deployment and configuration | 2 | 12.1 | 2026-09-23 | 2026-09-25 | DevOps Engineer, Cloud Engineer
12.3 | Production data migration execution | 2 | 12.2 | 2026-09-28 | 2026-09-29 | Database Engineer, DevOps Engineer
12.4 | Go-live support and monitoring | 2 | 12.3 | 2026-09-30 | 2026-10-01 | Project Manager, Solution Architect, DevOps Engineer
12.5 | Initial user support and issue resolution | 1 | 12.4 | 2026-10-02 | 2026-10-02 | Senior .NET Developer, Business Analyst
13 | Post Deployment Support | 45 |  | 2026-10-05 | 2026-12-04 | Project Manager
13.1 | System Stabilisation and Handover Deliverables | 22 |  | 2026-10-05 | 2026-11-03 | Project Manager
13.1.1 | Final System Acceptance | 5 | 12.5 | 2026-10-05 | 2026-10-09 | Project Manager, Business Analyst, Client
13.1.2 | Operational Support Transition | 5 | 13.1.1 | 2026-10-12 | 2026-10-16 | Project Manager, DevOps Engineer
13.1.3 | Final Technical Documentation Set | 12 | 13.1.2 | 2026-10-19 | 2026-11-03 | Solution Architect, Senior .NET Developer
13.2 | Knowledge Transfer and Sustainability | 20 |  | 2026-10-19 | 2026-11-13 | Project Manager
13.2.1 | Train-the-Trainer Programme | 7 | 13.1.2 | 2026-10-19 | 2026-10-27 | Project Manager, Business Analyst, Senior .NET Developer
13.2.2 | Completed Knowledge Repository | 7 | 13.2.1 | 2026-10-28 | 2026-11-05 | Project Manager, Business Analyst
13.2.3 | Mentorship Completion Records | 6 | 13.2.2 | 2026-11-06 | 2026-11-13 | Project Manager, Business Analyst
13.3 | Monitoring and Evaluation Outputs | 15 |  | 2026-10-28 | 2026-11-17 | Project Manager
13.3.1 | Dissemination Effectiveness Report | 8 | 13.2.1 | 2026-10-28 | 2026-11-06 | Project Manager, Business Analyst
13.3.2 | Community of Practice (CoP) Output | 7 | 13.3.1 | 2026-11-09 | 2026-11-17 | Project Manager, Business Analyst
13.4 | Project Closure Outputs | 15 |  | 2026-11-16 | 2026-12-04 | Project Manager
13.4.1 | Final Project Report | 10 | 13.2.3 | 2026-11-16 | 2026-11-27 | Project Manager
13.4.2 | Financial Closeout Documentation | 5 | 13.4.1 | 2026-11-30 | 2026-12-04 | Project Manager